## Sheet1
Use case | Priority (10, 20,30,40, 50) 10 is highest, 50 is lowest | Time Estimate (.5 1,2,3,5,8,20,40,100) this is in Hours
As a user, I want to create an account so that I can securely log in and access my expense data. | 10 | 20
As a user, I want to categorize my expenses (e.g., food, transportation, entertainment) so that I can see where my money is going. | 20 | 12
As a user, I want to import expense data from a CSV file so that I can easily migrate my data from other applications. | 40 | 40
As a user, I want to generate reports (e.g., monthly, yearly) so that I can analyze my financial data over time. | 30 | 40
As a user, I want to export my expense data to a CSV file so that I can back it up or analyze it in other tools. | 50 | 12
As a user, I want to set up recurring expenses (e.g., rent, subscriptions) so that I don’t have to manually enter them every month. | 20 | 24
As a user, I want to see charts and graphs of my expenses so that I can easily visualize my spending patterns. | 30 | 40
As a user, I want to create custom categories so that I can organize my expenses in a way that makes sense to me. | 30 | 24
As a user, I want to log in using my email and password so that I can access my account. | 10 | 20
As a user, I want to add a new expense with details like amount, category, and date so that I can keep track of my spending. | 20 | 8
As a user, I want to edit an existing expense so that I can correct any mistakes or update information. | 20 | 8
As a user, I want to set a budget for different categories so that I can control my spending. | 20 | 24
As a user, I want to view a summary of my expenses for a selected time period so that I can understand my spending habits. | 30 | 16
As a user, I want to receive notifications when I am close to exceeding my budget so that I can adjust my spending accordingly. | 40 | 24
As a user, I want to view and manage my recurring expenses so that I can keep track of my regular payments. | 40 | 20
As a user, I want to filter the data by category, date, or amount so that I can focus on specific aspects of my spending. | 30 | 16
As a user, I want to delete an expense so that I can remove any incorrect or unnecessary entries. | 20 | 8